## Tasks
Hamfest 2008 - Task list with dates
Date | Task | Status
2007-10-15 | Reserve Hamfest date for next year | Done- contract completed by auditorium
2008-06-29 | Contacted by Sam Adams | Sam wants inside space this year for his racks
mid - July | Start major activities | Three months before hamfest
2008-07-14 | Reviewed Vendor List | Time to start contacting vendors- 3 mo to hamfest
2008-07-14 | Called CT Morgan | Barbara- still plan to come, followed up via email
2008-07-14 | Called Richard Stubbs at MFJ | They are cutting back and will not attend this year
2008-07-14 | Email WC4H, Carl Herrera | Richard says he is new dealer in Miami - inivte
2008-07-14 | Emailed Sherri Brower | Checked reco on youth, card checking,
2008-07-14 | Updated our handout flyer | Got draft reviewed by several people
2008-07-14 | Updated the web flyer | Got web flyer to Don to put on the web with links
2008-07-14 | Called area hotels to get prices | Got several hotels to give us event pricing
2008-07-14 | PCARS meeting-check team leads | Met with Kathy Q, and others to verify support
2008-07-15 | Continued updating hotel info | Added Residence Inn
2008-07-15 | Tedco - called Ted about tickets | Ted will pay again for printing & wants same booth
2008-07-15 | Called Flamingo Printers-tickets | Stacy - updated info over phone- will email proof
2008-07-15 | Emailed Gail Innone at ARRL | Checked on possible ARRL Hq rep/speaker
2008-07-22 | Picked up the tickets from printer | Flamingo had charged us tax-I did not notice it then
2008-07-26 | Emailed tax certificate to Flamingo | Asked them to adjust the invoice
2008-07-30 | Sam Adams called about space | Wants east wall - said Del Danko passed away
2008-07-31 | Got the Flamingo invoice straight | Dave had the invoice paid
2008-08-01 | Called Judy Danko-Discount Product | Left here a voice mail. Sent email which bounced
2008-08-01 | Called Ft Pierce ARC - mailed request | Got PCARS table for 9 Aug for tickets and flyers
2008-08-01 | Called Ray Kassis-EC about EBC-1 | Cleared up bad info to them about space charge-cleared the air and confirmed him for ARES booth
2008-08-05 | Contacted by Carl Herrera WC4H | Miami MFJ dealer referred to us by MFJ. He will take a booth in the front of the stage. Www.WC4H.com
2008-08-05 | Contacted Richard Stubbs at MFJ | Got quote on MFJ-259B as hamfest prize. Need to send letter and check. He will also send us catalogs and MFJ door prizes.email mfjcustserv@mfjenterprises.com
2008-08-06 | Printed flyers for Ft Pierce Hamfest | Printed 200 flyers. Picked up banner at club station. Got 50 tickets to go with Clayton to PCARS table at Ft Pierce hamfest this Saturday.
2008-08-07 | Emailed Hamfest info to CQ Magazine | Send information to cq@cq-amateur-radio.com See message in Hamfest binder.
2008-08-07 | Submitted info for World Radio Mag | Went online to www.wr6wr.com and then to Hamfest. At the bottom of the list is button to submit info. See format in Hamfest binder.
2008-08-08 | Got flyers, banner & tickets to Clayton | Clayton taking these to Ft Pierce
2008-08-09 | Ft Pierce Hamfest | Clayton sold 19 tickets and gave out many flyers. He is bringing others to club meeting Monday.
2008-08-10 | Called Cal Smith - WA4KLL | Cal in Rockledge wants his same 60 feet of swap area. I emailed him the form.
2008-08-10 | Contacted Bill Gallier, W4WX | Sent Bill a copy of our flyer to get distributed to the Jacksonville clubs and on their websites.
2008-08-10 | Sent info to IRARC & HIARC | Got flyer and ticket sale info to these two local clubs.
2008-08-10 | Email to Dan - K1TO | Trying to coordinate the FCG meeting for hamfest. Also requested if he know of a good ARRL Rep to request.
2008-08-11 | Judy Danko-Discount products | She called and confirmed she wants same tables.
2008-08-11 | Quote for Sam Adams - emailed | Completed quote for Satellite TV HQ for Sam Adams. Tables 129 & !30 plus 50 feet of rack space for $200
2008-08-11 | Contacted CGA - Dave Nuebauer | Called and left Dave a message. Then emailed him info with a flyer and vendor registration form. Will follow up. He called back from Canada and wants same booth as last year.
2008-08-11 | Contacted Tower Electronics | Called and left Scott and Jill a message. They are on the hamfest circuit. Sent them an email proposal to give them more space inside the booth. Exchanged several emails with Jill and confirmed them with the modified booth. Provided the information to Don.
2008-08-11 | Contacted GAP Antennas | Called and talked to Chris. They will take same booth as last year-W. Sent letter of confirmation at Chris request.
2008-08-11 | Confirmation letter to CT Morgan | Mailed a letter confirming their booth with flyer.
2008-08-12 | Blue Star Antennas | Contacted Bob via email and got confirmation that he wanted the same booth in the West wing they had last year 111-113A for $100.
2008-08-12 | ALLTECH Computers | Sent an email to Marleine to see if she wanted to come back this year. She took 7 tables ($140) last year.
2008-08-12 | STARTEC International | Sent Fred Hufft, W4PLM, a letter to see if he wanted a booth again this year. Told him we would move him away from AMR.
2008-08-12 | Dangerous Engineering/OK Test | Contacted them to see if they wanted a booth this year. The booth they had last year will be The Sign Man. Offered them a similar booth on other side of the main room.
2008-08-12 | Publicity | Sent a note to BOD stating that I would let Dan Fisher our PIO take care of all local publicity. I had put in QST, CQ and World Radio. I also sent an email with an announcement to Sherri to include in her monthly mail to members in SFL.
2008-08-13 | Invited ARRL Section/Division Mgrs | Sent letters with a complementary ticket (no Stub) to the three Florida Section Managers and the SE Division Director.
2008-08-13 | The Sign Man - Rick | Sent Rick an email with the vendor form for his booth. Got a reply back today that he was sending it on to his wife to complete and forward to us.
2008-08-13 | ESRC1 Corp - Stanley Winston | Contacted Stanley by phone. He wansts his same booth in the west room. Sent him a vendor form and flyer-$180.
2008-08-13 | B&M Distributors - Jim K4LIX | Contacted Jim by email. He wants his same tables in the west room. Sent him a form to complete.
2008-08-13 | Mass Email Project | Sent sample message to BOD and asked for help in sending out the email messages.
2008-08-15 | Got ticket stubs to be mailed out | Ed Messer, Dave Hoilman, George and Arnie took 350 stubs to get canned email message sent to hams.
2008-08-15 | Website update | I worked on updating files for the website including, Forums, floor plan, ARES Badging, ARRL card checking, and got them to Don who updated and put on website
2008-08-16 | Email former table holders | Sent email message and flyer to all people who bought tables last year who gave me email addresses.
2008-08-17 | Email ARRL clubs | Sent email messages to contact people in 109 ARRL affiliated clubs in FL. Went to the ARRL.org site then to clubs and opened each one. Copied email addresses to the message and sent in groups of about ten at a time.
2008-08-20 | DNPDecals-request | Got email from DNP requesting info on a booth. Sent info and they want booth R. Will send check.
2008-08-21 | AMR Computer parts | Received call from Anna - Wants 3 tables. Sending check.
2008-08-25 | PACCOM | Dave Frey checked and they have a conflict this year. Added them to the list for next year.
2008-08-25 | Commercial vendors-Dennis O'quinn | Dennis mailed letters to several commercial vendors who might be interested in the hamfest.
2008-08-26 | PO Mail pickup | Picked up mail and received several checks and table requests including check from Tower Electronics.
2008-08-29 | Table request processing | Completed processing table requests on hand. Gave Dave over $800 in checks to deposit.
2008-08-29 | Ticket stub processing | Gave George 200 more ticket stubs to email messages and flyers.
2008-09-29 | MFJ Prizes | Received the MFJ-259B 2nd place prize and 8 MFJ speakers to be given as door prizes.
2008-08-29 | Forum Schedule | Updated schedule with Packet forum and FCG meeting.
2008-08-30 | PO Mail pickup | Picked up mail and received several table and ticket requests. Processed them.
2008-09-01 | New vendors | Sent email packages to ProStar Batteries in S.FL., HamStick, & DownEast microwave. Downeast bounced. Will follow up with other two this week.
2008-09-02 | Certificate of Insurance | Filled out form and sent letter requesting a certificate of insurance for the auditorium. This is a must. Just fill out application form like the previous year.
2008-09-02 | World Radio Magazine | Received six free subscriptions for WRM for door prizes as a result of registering our hamfest.
2008-09-03 | Main Prizes | Called Tom Morgan and emailed info to order the ICOM main prizes for the hamfest. Also sent lodging info and a flyer for them to put up.
2008-09-03 | ARRL HQ Representative | Emailed Katie Breen and got confirmation that Jackie Cornell will be our ARRL HQ representative.
2008-09-03 | Reliable Poly John | Waste management sold portable toilet business. Contacted Tiffany at the new company. Sent her our former agreement, map and tax exempt form. They will meet last years WM agreement.
2008-09-03 | M&B Golf Carts | Called Kevin at M&B and reserved the golf carts. He has email, so I will send all the information.
2008-09-04 | G&S Security | Called and talked to Harley Gibbons and requested quote for overnight security at the hamfest.
2008-09-04 | Door Security - Young Marines | Called Greg Voors - message-finally got in touch on 9/8 and they have boot camp that weekend.
2008-09-07 | Email flyers | Emailed flyers from about 50 ticket stubs that Arnie could not finish.
2008-09-08 | STARTEK, International | Called Fred and got him signed up for three swap tables instead of a booth this year.
2008-09-08 | ProStar Batteries | Called Sam & Brenda in Miami. He will be in China for a month so they cannot come. We need to contact them earlier next year.
2008-09-08 | HamStick Antennas | Called Mike. He indicated interest in Orlando, but when I talked to him on the phone he was not interested.
2008-09-08 | Downeast Microwave | Sent direct email again to Steve. He contacted me and said he would not be inside because he does not really have product but he will be outside in the tailgate area and will give us a doorprize.
2008-09-08 | FL contest Gp, K1TO | Talked to Dan to clarify things about the forum, lunch and meeting. Took his info and emailed direct to 214 members. Don got me the email list by copying it from the web site and putting it in Excel.
2008-09-08 | PCARS Meeting - security/tickets | Had PCARS meeting. Margaret sold 25 tickets. I also sold two tables and additional tickets. I gave an update and passed around a signup sheet for security. Really need someone to head up security.
2008-09-09 | ARRL HQ Representative | Called Jackie Cornell and asked her to send me a short writeup about her presentation so I could link it to the forum list on the website.
2008-09-09 | Youth activities | Sent email to Emily and Mike Bishop regarding the youth activities. Decided to set up tables in the entrance area for the youth. Need to send tickets to Emily and Mike Bishop.
2008-09-09 | Auditiorium | Called Ron Hayes to discuss setup and availablilty. He said the senior day is still the Friday before us so we will not be able to set up before 6:00PM. I also need to fill out the Special Activity Application. Also, the City is now charging $10 each for barricades.
2008-09-09 | Auditorium Barricades | Contacted Tim for information about barricades. Ron and I calculated the need for 11 barricades, 6 across front, 2 front of parking on Lake, 3 at middle entrance. Tim wants 15 barricades.
2008-09-09 | Auditorium Concession | Contacted Denver Cline, 258-2704, and he will have food available on Friday from 6:00PM to 9:00PM.
2008-09-09 | Auditorium ATM Machine | Called Bill Page, Sport Shows Specialist, 777-7455 to get info. Left voice mail.
2008-09-10 | PEET BROS - Weather instruments | Called PeetBros in St. Cloud. Had flyer from Orlando. Added to vendor list, emailed info. Need follow up call if I do not hear back.
2008-09-10 | Batteries America | Send Ed Youst an email package. Need to follow up if I do not hear from them.
2008-09-10 | On the Spot Embroidery | Called OTSembroidery in Deland. They are in Ohio. Myrna is interested, but having surgery next week. Will let me know after talking to doctor. Sent email package.
2008-09-11 | Auditorium - Special Activity app | Went to auditorium and and filled out the application. I should have done this sooner, but they missed this. While there I talked to Gus who does the setup. He has a dolly that we can use.
2008-09-12 | Sent complimentary tickets | Sent tickets to Jackie Cornell, ARRL HQ, and Emily Bishop, Youth coordinator along with Emily's father.
2008-09-12 | Processed ticket requests | Sent out several table and ticket requests.
2008-09-12 | Ordered Table Skirts | Counted up need for table skirts and went to Party City and ordered 40 royal blue table skirts. They are giving us a 30% discount. Pick up early October
2008-09-12 | Forum descriptions | Worked with forum leaders to get input for descriptions to their forums. Worked with Don who is putting links to the forums on the web so people can read the descriptions.
2008-09-13 | Checked hamfest supplies | Went to club station and went through the hamfest supplies from last year. Also checked equipment that was left for sale from last year.
2008-09-13 | Door prizes | Went to Harbor Freight and bought ten digital multimeters they had on sale for $2.09 each.
2008-09-15 | Insurance Certificate | Picked up mail and received two copies of our insurance certificate along with form to apply for next year. This took two weeks.
2008-09-17 | Processed ticket requests | Sent our several ticket and table requests. Used the same stamp on the back of tickets with no stubs to send for commercial booths. Including an instruction note in each one.
2008-09-17 | Peet & Batteries America | Called PeetBros. No interest this year. Called Batteries America and waiting for a call back.
2008-09-17 | Swap table follow up messages | Sent follow-up email messages to 27 people who had tables last year that we did not hear from yet this year. Also started making phone calls to those with no email addresses. It is important to try to get email addresses for all swap table vendors as it makes follow up the next year so easy.
2008-09-22 | Checked mail - processed | Picked up mail and processed some ticket requests.
2008-09-22 | ATM Machine-Cash-to-Go | Called Stuart Ellison, 407-276-4026, to see if he would put an ATM machine at the auditorium during the hamfest. He is interested and will call back to let me know if he has a machine available.
2008-09-23 | On the Spot Embroidery | Got a call from Gerald Barson 937-554-2027. He and his wife do want to come to the show. He wants a 20 foot booth. I sent him information offering him a booth in front of the stage.
2008-09-23 | Batteries Plus | Called Batteries Plus on N. Wickham, 752-4984. Left message for owner. Was finally able to contact him later. Maybe next year. No time to prepare this year.
2008-09-25 | Cash-to-Go ATM Machine | Confirmed that they will have a machine at the hamfest.
2008-09-29 | City of Melbourne | Called Cindy Bragg at 953-6278 to check status of our Non-business Tax Receipt form required for the Melbourne Auditiorium. I submitted it on 2 Sep. Left voice mail.
2008-09-30 | BOD Meeting | Met with BOD. Discussed status of hamfest. They wanted to present a plaque for Ted Woodbury W4LR.
2008-09-30 | Checked mail - processed | Picked up mail and processed some ticket requests.
2008-10-01 | Table skirts - Party City | Called to verify they would have the table skirts. The manager had not gotten the order I placed on 9/12/08. He will order and call me. 729-8711
2008-10-01 | Al's Trophy Shop | Went to Al's and ordered plaque for Ted.
2008-10-01 | Forum projector/screen | Contacted Jim Long and he will bring a projector for the weekend. Don will bring the other one. I asked Jim to see if he could find a portable screen.
2008-10-01 | NWS Electronics - Miami | Returned call to Sid. He would like a block of 7 tables, but wants the block with 138-142 end rather than the other end he had last year. Have call in to Tom Johnson to see if I can arrange something with him since he has 139-140.
2008-10-02 | Security/screen | Jim Long sent security update and has found a possible screen. Jeff Heldrith will try to get the one he borrowed for us last year.
2008-10-02 | Titusville ARC-Sherry Ferguson | Called to verify they still want the three tables she asked for. Yes they do. She has sold 20 tickets so far. She said Abell does not want a table, but Husband wants 2 tables. I have not yet received the order.
2008-10-02 | Tom Shedd K4IWD | Tom called about a table & tickets. Emailed him form and info. He is mailing it in.
2008-10-03 | Checked mail - processed | Picked up mail and processed some ticket requests. Also got table request from Tom Shedd
2008-10-06 | Confirmations for services | Called Golf Cart rental, overnight security and portable toilet providers and confirmed all of them for Hamfest.
2008-10-07 | Florida Dept of Revenue | Received a call from Michele Elkins requesting info on vendors at our hamfest. We told her we could provide information on commercial vendors, but that we do not keep records on our tailgate/swap vendors. I told her that as in the past we would pass out the required forms to all the vendors and they would be responsible for collecting the sales tax.
2008-10-08 | Florida Dept of Revenue | Received forms from the dept of revenue
2008-10-08 | NWS Electronics - Miami | Tom Johnson cannot use his tables due to family emergency. Sold that block of tables to Sid. Will reimburse Tom his $40.
2008-10-09 | Cal Smith | Cal left a voice message that he cannot attend due to a fall and broken ribs. He has a large block of tables. Will try to resell the tables.
2008-10-09 | Floor plan layout | Worked with Don on the phone to re-layout the floor plan so that we put more swap tables in place of the booths that were not sold. I marked all the tables that were six foot tables and 8 foot tables. Also marked the drapes and put the number of chairs to be set up in each row. I took this to the auditorium and went over it with Ron Hayes.
2008-10-09 | Table skirts - Party City | Went to Party City and picked up the table skirts. They are $5.95 ea. They give discount of 30% for over $200. They were only able to get 33 skirts, so it came to about $190. They still gave us the 30% discount.
2008-10-10 | CT Morgan | Tom called at noon and said they were not going to be able to come down to the hamfest. The excuse was that they were too busy with business and did not have time to pack the truck and come down. This was very disappointing and there was nothing we could do about it at that late time.
2008-10-10 | Rich Margey KE1DH T-shirt man | Moved Rich from end tables 1&2 to booth D1-D3 as a favor to him and to help us better fill up the auditorium. Rich recently lost his job and also was not able to go to Dayton, so he had a big stock.
2008-10-10 | Tailgate & Setup | Went down to auditorium at about 3:00PM. Golf carts came on time. Portable toilets did not come until about 5:30PM which caused a problem for some people. We were not able to get into the auditiorium at all until 6:00PM.
10/1012008 | ATM Machine-Cash-to-Go | They brought the machine about 7-8PM. Set it up and working. During the night the screen went blank. Sat AM I tried calling their number and go no reply. I then called the toll free number on the front of the machine and they had me reboot the machine which solved the problem. It worked fine the rest of the weekend. They picked the machine up about 1:00PM on Sunday.
2008-10-10 | PCARS Consignment Booth | To compensate for loss of CT Morgan we moved the PCARS Consignment booth to his booth. That filled up that corner.
2008-10-10 | Parking lot setup - John Azzolina | John came out about 3:30PM. His usual crew was unable to help. We put a note out on email and got him several volunteers to set up the parking lot.
2008-10-10 | Table skirts - setup | Jim Armstrong and his wife installed the table skirts on tables needed. We had several left over this year.
2008-10-10 | Table numbering | One of the club members put post-it stickers on each table with the numbers.
2008-10-11 | ARES Tables | Ray wanted one extra table to sell some stuff that he had. We took one table out of the original PCARS booth and relocated Ray to that booth. We put table skirts on it and left them at 8 foot tables. We folded up the two tables X&Y by the food concession and did not use them.
2008-10-11 | On the Spot Embroidery | On Friday night our team helped them move in. It was a lot of work. By Saturday afternoon Gerry was sick. They closed and left early. They did not come to open on Sunday. Myrna and her son came and we helped pack them up. Then they left and were going to take Gerry to the clinic. They were not very busy on Saturday.
2008-10-12 | Grand Prize drawings | Held the drawings at 1:30PM. The first place winner was in Melbourne and came to pick up the prize. Second place was in Cocoa and a friend delivered it.
2008-10-13 | Auditorium update | Went to auditorium. Complained about the barriers not having working lights. Ron will cut price in half. This year they are charging $10 each. In past they were free. Picked up printer that testing group had left there.
2008-10-13 | Prize shipping | Packed third and fourth place prizes and sent them via USPS priority mail.
2008-10-17 | Sun Bank issue | Dave reported an issue with Sun Bank. They did not post our two deposits of over $9K from the weekend. He contacted them and they said the money was taken to Orlando from weekend pickups. They did not know where our deposits were, but they would find them. Dave was upset with their attitude. It took several phone calls and a personal trip to the bank to get this resolved.
2008-10-17 | G&S Security Payment | Received bill for the security. It had tax. Scanned and emailed invoice to Dave H. Sent G&S Security our tax exempt form and had Dave initiate payment.
2008-10-23 | Auditirium final payment/deposit | Received final bill and deposit invoice. They had tax on them. Called Sandy. She had our tax form in 2007 file and forgot. I corrected the invoices, scanned and emailed to Dave. Then I sent a letter with the corrected invoices to the auditorium. Dave is initating payment by the bank.