## Schedule-2013
Task | Lead | Start Date | Finish Date | Status %
Auditorium reserved |  |  |  | 100
Review auditorium lease |  |  |  | 80
Apply to be the ARRL Florida State Convention |  |  |  | 100
ARRL website contact info-update |  |  |  | 50
Hamfest Flyer (1 page, b&w)-update |  | 2013-04-15 | 2013-07-01 | 0
Establish e-mail address:hamfest 2013@pcars.org |  | 2013-03-01 | 2013-04-01 | 100
Hamfest website: update with new info |  | 2013-04-15 | 2013-09-01 | 0
E-Mail: review lists of e-mail addresses |  | 2013-05-01 | 2013-07-01 | 100
Hamfest Flyer(multi-page, color): e-mail to Vendors, with cover letter: July |  | 2013-07-13 | 2013-07-16
August |  | 2013-08-17 | 2013-09-07
September |  | 2013-09-14 | 2013-09-24
Hamfest Flyer (multi-page, color): e-mail to past Attendees, with cover letter: July |  | 2013-07-13 | 2013-07-16
August |  | 2013-08-17 | 2013-09-07
September |  | 2013-09-14 | 2013-09-24
Hamfest Flyer: e-mail to Clubs, with cover letter |  | 2013-07-13 | 2013-08-30
Tables reserved: based on sale of 209 tables |  |  | 2013-10-05
Tables payed for: based on sale of 209 tables |  |  | 2013-10-05
Certificate of liability insurance; obtain |  | 2013-07-18 | 2013-08-01
Consumer's Certificate of Exemption: determined to not be necessary!
Tickets-purchase |  | 2013-07-23 | 2013-07-30
Tickets-sale of: based on sale of 1500 |  | 2013-08-01 | 2013-10-05
Ticket booth: Staffing
Caterers-complete arrangements
Non-Business Tax Receipt Referral Form-complete and deliver to Aud. |  | 2013-08-01 | 2013-09-01
Advertise hamfest: ARRL (QST), CQ hamfest listing, World Radio (form), Florida Today
Tailgate: Print passes
Booth and swap tables: skirts, backdrops, dividers; purchase/obtain
Table layout, indoor: Review and finalize |  | 2013-06-01 | 2013-06-15
Hamfest Program: Compose and review. Print. |  | 2013-09-15 | 2013-10-01
Talk-in/On the Air: Staff and plan in place |  | 2013-08-15 | 2013-10-01
Forum/Meeting Rooms: print individual schedules for the rooms |  |  | 2013-10-05
Forums and Meetings arranged, host designated |  | 2015-07-01 | 2013-09-15
Technical presentations: Based on schedule of 5 1-hour presentations |  | 2013-07-01 | 2013-09-15
Parking: Staffing complete |  | 2013-09-01 | 2011-10-06
Consignment table: staff, and print consignment forms |  | 2013-09-01 | 2011-10-06
Amateur radio exams: staff, and arrange for materials |  | 2013-09-01 | 2011-10-06
ARES Badging: staff |  | 2013-09-01 | 2011-10-06
ARRL Awards checking: staff |  | 2013-09-01 | 2011-10-06
Prizes: Purchase/Solicit Main Prizes |  | 2013-07-15 | 2013-09-15
Prizes: Solicit hourly door prizes |  | 2013-07-15 | 2013-10-13
Hotels: check that website info is current and accurate |  | 2013-06-15 | 2013-07-15
RV sites: check that website info is current and accurate |  | 2013-07-11 | 2013-07-15
Security: Arrange for with outside agency |  | 2013-07-15 | 2013-08-15
Security: Enlist help of Young Marines |  | 2013-07-25 | 2013-08-26
BETA Club: Sunday door security |  | 2013-07-25 | 2013-08-26
Golf carts: rental |  | 2013-09-01 | 2013-09-15
Portable toilets: rental of 1 regular and 1 handicapped |  | 2013-09-01 | 2013-09-15
Parking barriers |  | 2013-09-01 | 2013-09-15
Dumpster: have one delivered |  | 2013-09-01 | 2013-09-15
BEARS Vehicle: Arrange for its presence
Pay balance of Auditorium Contract: $1594.50 |  | 2013-09-10 | 2013-09-14
FL. Dep. Of Revenue: print their form |  | 2013-09-25 | 2013-10-01
FL. Dep. of Revenue: provide list of vendors |  | 2013-10-13 | 2013-10-19
Reserve auditorium for next year |  | 2013-10-15 | 2013-10-18
Thank you letters |  | 2013-10-21 | 2013-10-31
Update e-mail lists from vendor forms and ticket stubs |  | 2013-10-15 | 2013-10-19
E-mail survey to attendees

## Schedule-2012
Task | Lead | Start Date | Finish Date | Status %
Auditorium reserved |  |  |  | 100
Review auditorium lease |  |  |  | 100
Apply to be the ARRL Florida State Convention |  |  |  | 100
ARRL website contact info-update |  |  |  | 100
Hamfest Flyer (1 page, b&w)-update |  | 2012-04-15 | 2012-07-01 | 100
Establish e-mail address:hamfest 2012@pcars.org |  | 2012-03-01 | 2012-04-01 | 100
Hamfest website: update with new info |  | 2012-04-15 | 2012-09-01 | 100
E-Mail: review lists of e-mail addresses |  | 2012-05-01 | 2012-07-01 | 100
Hamfest Flyer(multi-page, color): e-mail to Vendors, with cover letter: July |  | 2012-07-13 | 2012-07-16 | 100
August |  | 2012-08-17 | 2012-09-07 | -
September |  | 2012-09-14 | 2012-09-24 | -
Hamfest Flyer (multi-page, color): e-mail to past Attendees, with cover letter: July |  | 2012-07-13 | 2012-07-16 | 100
August |  | 2012-08-17 | 2012-09-07 | -
September |  | 2012-09-14 | 2012-09-24 | 100
Hamfest Flyer: e-mail to Clubs, with cover letter |  | 2012-07-13 | 2012-08-30 | -
Tables reserved: based on sale of 209 tables |  |  | 2012-10-05 | 93
Tables payed for: based on sale of 209 tables |  |  | 2012-10-05 | 73
Certificate of liability insurance; obtain |  | 2012-07-18 | 2012-08-01 | 100
Consumer's Certificate of Exemption: determined to not be necessary! |  |  |  | -
Tickets-purchase |  | 2012-07-23 | 2012-07-30 | 100
Tickets-sale of: based on sale of 1500 |  | 2012-08-01 | 2012-10-05 | 16
Ticket booth: Staffing |  |  |  | 100
Caterers-complete arrangements |  |  |  | 100
Non-Business Tax Receipt Referral Form-complete and deliver to Aud. |  | 2012-08-01 | 2012-09-01 | 100
Advertise hamfest: ARRL (QST), CQ hamfest listing, World Radio (form), Florida Today
Tailgate: Print passes |  |  |  | 100
Booth and swap tables: skirts, backdrops, dividers; purchase/obtain |  |  |  | 80
Table layout, indoor: Review and finalize |  | 2012-06-01 | 2012-06-15 | 100
Hamfest Program: Compose and review. Print. |  | 2012-09-15 | 2012-10-01
Talk-in/On the Air: Staff and plan in place |  | 2012-08-15 | 2012-10-01 | 100
Forum/Meeting Rooms: print individual schedules for the rooms |  |  | 2012-10-05
Forums and Meetings arranged, host designated |  | 2015-07-01 | 2012-09-15 | 100
Technical presentations: Based on schedule of 5 1-hour presentations |  | 2012-07-01 | 2012-09-15 | 80
Parking: Staffing complete |  | 2012-09-01 | 2011-10-06 | 100
Consignment table: staff, and print consignment forms |  | 2012-09-01 | 2011-10-06
Amateur radio exams: staff, and arrange for materials |  | 2012-09-01 | 2011-10-06 | 100
ARES Badging: staff |  | 2012-09-01 | 2011-10-06 | 100
ARRL Awards checking: staff |  | 2012-09-01 | 2011-10-06 | 100
Prizes: Purchase/Solicit Main Prizes |  | 2012-07-15 | 2012-09-15 | 100
Prizes: Solicit hourly door prizes |  | 2012-07-15 | 2012-10-13
Hotels: check that website info is current and accurate |  | 2012-06-15 | 2012-07-15 | 100
RV sites: check that website info is current and accurate |  | 2012-07-11 | 2012-07-15 | 100
Security: Arrange for with outside agency |  | 2012-07-15 | 2012-08-15 | 100
Security: Enlist help of Young Marines |  | 2012-07-25 | 2012-08-26 | 100
BETA Club: Sunday door security |  | 2012-07-25 | 2012-08-26 | -
Golf carts: rental |  | 2012-09-01 | 2012-09-15 | 100
Portable toilets: rental of 1 regular and 1 handicapped |  | 2012-09-01 | 2012-09-15 | 100
Parking barriers |  | 2012-09-01 | 2012-09-15 | 100
Dumpster: have one delivered |  | 2012-09-01 | 2012-09-15 | 100
BEARS Vehicle: Arrange for its presence |  |  |  | 100
Pay balance of Auditorium Contract: $1594.50 |  | 2012-09-10 | 2012-09-14 | 100
FL. Dep. Of Revenue: print their form |  | 2012-09-25 | 2012-10-01 | 100
FL. Dep. of Revenue: provide list of vendors |  | 2012-10-12 | 2012-10-19
Reserve auditorium for next year |  | 2012-10-15 | 2012-10-18
Thank you letters |  | 2012-10-21 | 2012-10-31
Update e-mail lists from vendor forms and ticket stubs |  | 2012-10-15 | 2012-10-19
E-mail survey to attendees